## Report
Project Stream | Complaints Management System | Project Full Name | Complaints Management System
Individuals | Csaba Riedlinger | Project Manager | Bally Hayer
| Zog Gibbens | Project Status | Please select the appropriate status from the list | Development
|  | Estimated Days Remaining | Please indicate number of days remaining | 60
|  | Project Completion % | Please indicate the amount of budget consumed as a percentage | 50%
Review Date | 2014-05-15 | 2014-04-29 | 2014-03-28
Progress Tagline | Mapping for lookup tables now almost complete. 3 completely finished, one nearing completion. Response on remaining items expected by 23/05. Final merge of data is reliant on this being completed. | No progress at all on the compliance report - flagged to Kathi for escalation. Mapping of objects into complaints model completed by ZG. CR development of imports completed. | Development of Complaints Compliance report has been progressing. AML created, but no work on OBI due to upcoming 11g upgrade. Passed to Ops MI (Carla) for UAT (see issue below).
| Sales compliance flag is still an open issue. Waiting response from Andrew Blisset & David Hardy. Melanie aware of issue and pushing for response. First session held with OE contact for batch set up. Further sessions to be held over next few week. | Mapping for lookup tables now required (one complete with three more to do). Discussion around sales complaints flag due by 02/05. This could result in more work (small change). Final merge of data from two source systems still required - meeting with Melanie on 28/04 to discuss rules. | Latest ERD diagram received on Monday 24/03. Significant changes from previous diagram. ZG to analyse and map objects into our complaints model by 04/04.
| Wiki documentation progressing and is almost complete. Needs to be added into correct location and format. This will be done by end of 23/05. Final code review to take place following completion. System testing awaiting completion - Csaba will chase by 16/05. Session to be arranged with BIS Security team to discuss revoking access to old tables post go live. This will prevent users from using out of date information. | Wiki documentation still required. This will be set up by 02/05. | CR to load data from complaints test environment into D01 environment for internal testing and to enable build process for new batch process by 02/04.
Successes | Issue around closed complaints fully resolved | Half way through system testing, very few problems to date, all of which immediately resolved. | 2 dashboard designs presented to COLG last week. This reduces BAU manual reporting requirements. Dashboards will now be passed over to Ops MI for final development and ownership - waiting response to agree handover date.
Issues | OFGEM reporting dates - issue with re-opened complaints using the original created date rather than the date it was reopened. This is outstanding due to holidays of key contacts. Progress expected by 23/05. | Issue with closed complaints, and how the financial data for these is reported. Fix identified and soon to be implemented, but this will lead to additional work to integrate this into new complaints ETL process. | Ops MI have not committed to UAT of Complaints Compliance report, as they are working on operational reporting deadlines. Raised as a risk with Rebecca Oates. Need to ensure Ops MI's workaround does not become the BAU report.
| Concerns around go-live process - some detail still required. Meeting arranged on 27/05 with Bally to discuss the importance of the plug-ins to the go live process. | OFGEM reporting dates - issue with re-opened complaints using the original created date rather than the date it was reopened. | Issues with Complaints Debt Report, and how prompts for filters are working. Issues is with consistency. ZG working to resolve by 28/03 as needs to be resolved before OBI freeze.
Concerns around go-live process - some detail still required. Meeting to be arranged with Bally to discuss the importance of the plug-ins to the go live process.

## Action List
Ref | Priority | Task | Resource | Status | Target Date | Start Date | Complete Date | Notes
1 | High | Maintain BIS BAU dependencies
1.1 |  | Identify D/W objects using complaints & spec changes | Zog | Complete |  | 2014-01-24 | 2014-01-28
1.2 |  | Apply code changes | Csaba | Complete |  | 2014-02-11 | 2014-03-06
1.3 |  | Test Code Changes | Csaba | Complete |  | 2014-02-11 | 2014-03-06
1.4 |  | Deploy changes to production | Csaba
2 | High | Convert non-OBI BAU to OBI
2.1 |  | Identify BAU Reporting for Conversion | OPS MI, Zog | Complete |  | 2014-01-24 | 2014-01-31
2.2 |  | Get copies of scripts and reports | Zog | Complete |  | 2014-02-13 | 2014-02-14
2.3 |  | Review scripts and reports and analyze | Zog | Complete |  | 2014-02-17 | 2014-02-21
2.4 |  | Build OBI prototypes if required | Zog | Complete |  | 2014-03-03 | 2014-03-19
2.5 |  | Complaints Ownership Time | Zog | Complete |  |  | 2014-04-01
2.5.1 |  | Design processes | Zog | Complete | 2014-03-11 | 2014-03-06 | 2014-03-10
2.5.2 |  | Develop processes | Zog | Complete | 2014-03-14 | 2014-03-11 | 2014-03-14
2.5.3 |  | Test processing | Zog | Complete | 2014-03-18 | 2014-03-17 | 2014-03-17
2.5.4 |  | UAT of new reporting | Zog, OPS MI, Credit |  |  | 2014-03-18 | 2014-03-18
2.5.5 |  | Deploy to production | Zog | Complete | 2014-03-25 | 2014-03-20 | 2014-04-01
2.5.6 |  | Batch running ok | Zog | Complete | 2014-03-26 |  | 2014-04-05
2.6 |  | Build Complaint Compliance Report |  | In Progress
2.6.1 |  | Design processes | Zog | Complete | 2014-03-11 | 2014-03-06 | 2014-03-10
2.6.2 |  | Develop processes | Csaba | Complete | 2014-03-18 | 2014-03-11 | 2014-03-24
2.6.3 |  | Test processing | Csaba | Complete | 2014-03-20 | 2014-03-11 | 2014-03-24
2.6.4 |  | UAT of new reporting | Csaba, OPS MI | With MI Team
2.6.5 |  | Deploy to production | Csaba
2.6.6 |  | Batch running ok | Csaba
2.7 |  | Build Weekly Summary Report | [5 empty] | With the addition of the compliance report, everything might be in OBI already
2.7.1 |  | Design processes | Zog | Complete |  | 2014-03-12 | 2014-03-19 | Provided demo on 19/03/2014. Main tweak was SLA's to completion times.
2.7.2 |  | Develop processes | Zog | Complete |  | 2014-03-12 | 2014-03-12
2.7.3 |  | Test processing | MI Team | In Progress
2.7.4 |  | UAT of new reporting | MI Team | In Progress
2.7.5 |  | Deploy to production | Zo | n/a
2.7.6 |  | Batch running ok | Zog | n/a
3 | Medium | Merge of new Complaints Model to Data Warehouse
3.1 |  | Identify key elements of existing solution + main tasks | Zog | Complete |  | 2014-02-03 | 2014-04-01
3.2 |  | Understanding of new tool and functionality | Zog, Csaba | Complete |  | 2014-02-03 | 2014-04-01
3.3 |  | Understanding of source schema | Zog, Csaba | Complete |  | 2014-02-03 | 2014-04-01
|  | Questions sent pertaining to how complaints are logged | Zog | Complete |  | 2014-02-07 | 2014-02-07
|  | Issue sent around start-end times and 1 second difference | Zog | Complete |  | 2014-02-11 | 2014-03-24 | 06-03-2014 email sent to chase up. No confirmed decision yet.
3.4 |  | HDS Set up (test) | Csaba | Complete |  | 2014-02-01 | 2014-04-01
3.5 |  | HDS set up (live) | Csaba/Dave
3.6 |  | Design new objects | Zog | Complete |  | 2014-04-01 | 2014-04-07
3.7 |  | Code new objects | Csaba | Complete |  | 2014-04-07 | 2014-04-20
3.8 |  | Test new objects | Csaba | Complete |  | 2014-04-07 | 2014-04-20
3.9 |  | System Test new and old | Zog, Csaba | In Progress
3.10 |  | UAT new and old | Zog, Csaba, OPS MI
3.11 |  | OBI Changes | Zog, Csaba |  |  |  |  | May need to make changes to DIM's, waiting on Mappings to be confirmed
3.12 |  | OBI Testing | OPS MI
3.13 |  | OBI Answers/Dashboards | OPS MI, Zog
3.14 |  | Deploy to production | Csaba
3.15 |  | Batch running ok | Csaba/Dave